## Housing Commissioner profr
STATEMENT SHOWING THE PROGRESS REPORT WITH PACKAGE WISE, STAGE WISE FOR CONSTRUCTION OF (G+3) PATTERN HOUSES UNDER JNNURM-BSUPHOUSING PROJECT (Rs.97.98 Cr. & Rs.97.97 Cr.) 3072 HOUSES AT AJITHSINGH NAGAR & KABELA AS ON 02-06-2012
Sl. No | Name of the Package | No. of blocks gounded | No. of units grounded | Piles foundation work in Blocks |  | Piles caps work in Blocks |  | Plinth beam work in Blocks |  | Columns work in floors |  | No. of Slabs |  | Brick work in Floors |  | Ceiling in floors |  | In side Plastering in floors |  | Out side Plastering in floors
|  |  |  | Tar get | Achievement | Tar get | Achievement | Tar get | Achievement | Tar get | Achievement | Tar get | Achievement | Tar get | Achievement | Target | Achievement | Tar get | Achievement | Tar get | Achievement
1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 11 | 18 | 11
Rs. 97.98 Cr.
1 | Ajithsingh Nagar Package-1 | 10 | 320 | 10 | 10 | 10 | 10 | 10 | 10 | 40 | 39 | 40 | 38 | 40 | 29 | 40 | 38 | 40 | 25 | 10 | 2
2 | Ajithsingh Nagar Package-2 | 12 | 384 | 12 | 12 | 12 | 12 | 12 | 12 | 48 | 44 | 48 | 43 | 48 | 37 | 48 | 38 | 48 | 28 | 12 | 2
3 | Ajithsingh Nagar Package-3 | 12 | 384 | 12 | 12 | 12 | 12 | 12 | 12 | 48 | 40 | 48 | 37 | 48 | 14 | 48 | 32 | 48 | 11 | 12 | 0
4 | Ajithsingh Nagar Package-4 | 8 | 256 | 8 | 8 | 8 | 12 | 8 | 8 | 32 | 21 | 32 | 19 | 32 | 2 | 32 | 18 | 32 | 2 | 8 | 0
5 | Ajithsingh Nagar Package-5 | 10 | 320 | 10 | 10 | 10 | 10 | 10 | 10 | 40 | 17 | 40 | 12 | 40 | 0 | 40 | 6 | 40 | 0 | 10 | 0
6 | Ajithsingh Nagar Package-6 | 12 | 384 | 12 | 12 | 12 | 12 | 12 | 12 | 48 | 28 | 48 | 21 | 48 | 0 | 48 | 17 | 48 | 0 | 12 | 0
7 | Ajithsingh Nagar Package-7 | 6 | 192 | 6 | 6 | 6 | 6 | 6 | 6 | 24 | 11 | 24 | 6 | 24 | 0 | 24 | 6 | 24 | 0 | 12 | 0
| Package-1,4, 5 & 7 (14 BLOCKS) | 14 | 448 | 14 | 13 | 14 | 6 | 14 | 0 | 56 | 0 | 56 | 0 | 56 | 0 | 56 | 0 | 56 | 0 | 14 | 0
| Total | 84 | 2688 | 84 | 83 | 84 | 80 | 84 | 70 | 336 | 200 | 336 | 176 | 336 | 82 | 336 | 155 | 336 | 66 | 90 | 4
Rs. 97.97 Cr.
8 | Kabela, Bhavanipuram Package-8 | 12 | 384 | 12 | 2 | 12 | 0 | 12 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0
| Total | 96 | 3072 | 96 | 85 | 96 | 80 | 96 | 70 | 384 | 200 | 384 | 176 | 384 | 82 | 384 | 155 | 384 | 66 | 138 | 4
[7 empty] | 76 |  | 70 |  | 205 |  | 178 |  | 78
Executive Engineer-VIII

## EE-8-Housing (02-06-2012)
No. of Packages = 8 | [5 empty] | VIJAYAWADA MUNICIPAL CORPORATION | [9 empty] | Items |  | Qty as per Est. | Upto Prev. week | This week | Total
No. of Blocks = 96 | [5 empty] | PROGRESS REPORT OF G+3 PATTERN HOUSES | [9 empty] | Piles |  | 13824 | 12129 | 553 | 12682
No.of Dwelling Units = 3072 | [5 empty] | PROJECTS (97.98 Cr. + 97.97 Cr.) | [9 empty] | Pile caps |  | 3456 | 2736 | 0 | 2736
Roof Slabs |  | Est. | Up to last week | This week | Total | AS ON 02-06-2012 CIRCLE -VIII | [9 empty] | Plinth Beams |  | 96 | 70 | 0 | 70
GF |  | 96 | 63 | 1 | 64 | [10 empty] | Columns |  | 13824 | 7128 | 252 | 7380
FF |  | 96 | 53 | 0 | 53 | [10 empty] | Roof Slabs |  | 384 | 176 | 2 | 178
SF |  | 96 | 35 | 0 | 35 | [10 empty] | Masonary Floors |  | 384 | 77 | 1 | 78
TF |  | 96 | 25 | 1 | 26
Sl. No. | Sector / Project cost | Name of Work |  |  |  | Name of Agency | Estimate Amount Rs. in Lakhs | Agmt. Amount | No. of Blocks | No. of Units | Date of Work order | Due Date | Target Date | Items | Quantity as per Estimate | Progress |  |  | Last Bill Date | Remarks
[16 empty] | Up to Last week | During the week | Total |  |  |  | 384
1 | BSUP-Housing Phase-I (97.98 Cr.) | Construction of G+3 pattern Houses under JNNURM - BSUP at Ajithsingh Nagar Near Sriram energy plant, Vijayawada, Package -1 |  |  |  | M/s.Vensar Constructions, Hyderabad | 960 | ` 7,18,23,204/- | 12 | 384 | 15/07/2010 | 14/10/2011 | 31/03/2012 | Piles | 1728 | 1728 | 0 | 1728 |  | RCC frame work and Brick work are in progress.
[14 empty] | Pile Caps | 432 | 432 | 0 | 432 |  |  |  |  | 252
[14 empty] | Plinth Beams | 12 | 10 | 0 | 10
[14 empty] | Columns - GF | 432 | 360 | 0 | 360
[14 empty] | Slabs - GF | 12 | 10 | 0 | 10
[14 empty] | Columns - FF | 432 | 360 | 0 | 360 |  |  |  |  | 12
[14 empty] | Slabs - FF | 12 | 10 | 0 | 10
[14 empty] | Columns - SF | 432 | 360 | 0 | 360
[14 empty] | Slabs - SF | 12 | 10 | 0 | 10
[14 empty] | Columns - TF | 432 | 360 | 0 | 360
[14 empty] | Slabs - TF | 12 | 9 | 0 | 9
[14 empty] | Masonary Floors | 48 | 26 | 1 | 27
2 |  | Construction of G+3 pattern Houses under JNNURM - BSUP at Ajithsingh Nagar Near Sriram energy plant, Vijayawada, Package -2 |  |  |  | M/s.Vensar Constructions, Hyderabad | 960 | ` 7,18,23,204/- | 12 | 384 | 15/07/2010 | 14/10/2011 | 31/03/2012 | Piles | 1728 | 1728 | 0 | 1728 |  | RCC frame & Brick Work are in progress.
[14 empty] | Pile Caps | 432 | 432 | 0 | 432
[14 empty] | Plinth Beams | 12 | 12 | 0 | 12
[14 empty] | Columns - GF | 432 | 432 | 0 | 432
[14 empty] | Slab- GF | 12 | 12 | 0 | 12
[14 empty] | Columns - FF | 432 | 396 | 36 | 432
[14 empty] | Slabs - FF | 12 | 11 | 0 | 11
[14 empty] | Columns - SF | 432 | 396 | 0 | 396
[14 empty] | Slabs SF | 12 | 10 | 0 | 10
[14 empty] | Columns - TF | 432 | 360 | 0 | 360
[14 empty] | Slabs TF | 12 | 10 | 0 | 10
[14 empty] | Masonary Floors | 48 | 35 | 0 | 35
3 |  | Construction of G+3 pattern Houses under JNNURM - BSUP at Ajithsingh Nagar Near Sriram energy plant, Vijayawada, Package -3 |  |  |  | M/s.Vensar Constructions, Hyderabad | 960 | ` 7,18,23,204/- | 12 | 384 | 15/07/2010 | 14/10/2011 | 31/03/2012 | Piles | 1728 | 1728 | 0 | 1728 |  | RCC frame & Brick Work are in progress.
[14 empty] | Pile Caps | 432 | 432 | 0 | 432
[14 empty] | Plinth Beams | 12 | 12 | 0 | 12
[14 empty] | Columns - GF | 432 | 396 | 0 | 396
[14 empty] | Slab- GF | 12 | 11 | 0 | 11
[14 empty] | Columns - FF | 432 | 396 | 0 | 396
[14 empty] | Slabs - FF | 12 | 11 | 0 | 11
[14 empty] | Columns - SF | 432 | 324 | 0 | 324 |  |  |  | 180
[14 empty] | Slabs - SF | 12 | 9 | 0 | 9
[14 empty] | Columns - TF | 432 | 288 | 36 | 324 |  |  |  |  | 324
[14 empty] | Slabs - TF | 12 | 6 | 0 | 6
[14 empty] | Masonary Floors | 48 | 14 | 0 | 14
4 | BSUP-Housing Phase-I (97.98 Cr.) | Construction of G+3 pattern Houses under JNNURM - BSUP at Ajithsingh Nagar Near Sriram energy plant, Vijayawada, Package -4 |  |  |  | M/s.Vensar Constructions, Hyderabad | 960 | ` 7,82,83,662/- | 12 | 384 | 22/2/2011 | 21/5/2012 | 21/05/2012 | Piles | 1728 | 1728 | 0 | 1728 |  | RCC frame & Brick Work are in progress.
[14 empty] | Pile Caps | 432 | 432 | 0 | 432
[14 empty] | Plinth Beams | 12 | 8 | 0 | 8 |  |  |  |  | 288
[14 empty] | Columns - GF | 432 | 252 | 36 | 288
[14 empty] | Slab- GF | 12 | 7 | 0 | 7
[14 empty] | Columns - FF | 432 | 252 | 0 | 252
[14 empty] | Slabs - FF | 12 | 7 | 0 | 7
[14 empty] | Columns - SF | 432 | 252 | 0 | 252
[14 empty] | Slabs - SF | 12 | 5 | 0 | 5
[14 empty] | Columns - TF | 432 | 0 | 36 | 36
[14 empty] | Slabs TF | 12 | 0 | 1 | 1
[14 empty] | Masonary Floors | 48 | 2 | 0 | 2
5 |  | Construction of G+3 pattern Houses under JNNURM - BSUP at Ajithsingh Nagar Near Sriram energy plant, Vijayawada, Package -5 |  |  |  | M/s.Vensar Constructions, Hyderabad | 960 | ` 7,82,83,662/- | 12 | 384 | 22/2/2011 | 21/5/2012 | 21/05/2012 | Piles | 1728 | 1728 | 0 | 1728 |  | RCC frame work are in progress
[14 empty] | Pile Caps | 432 | 360 | 0 | 360
[14 empty] | Plinth Beams | 12 | 10 | 0 | 10
[14 empty] | Columns - GF | 432 | 360 | 0 | 360
[14 empty] | Slab- GF | 12 | 9 | 0 | 9 |  |  |  |  | 1728
[14 empty] | Columns - FF | 432 | 252 | 0 | 252
[14 empty] | Slabs - FF | 12 | 3 | 0 | 3
[14 empty] | Columns -SF | 432 | 36 | 0 | 36
6 |  | Construction of G+3 pattern Houses under JNNURM - BSUP at Ajithsingh Nagar Near Sriram energy plant Vijayawada, Package -6 |  |  |  | M/s.Vensar Constructions, Hyderabad | 960 | ` 7,18,23,204/- | 12 | 384 | 15/07/2010 | 14/10/2011 | 31/03/2012 | Piles | 1728 | 1728 | 0 | 1728 |  | RCC frame work is in progress
[14 empty] | Pile Caps | 432 | 432 | 0 | 432
[14 empty] | Plinth Beams | 12 | 12 | 0 | 12
[14 empty] | Columns - GF | 432 | 432 | 0 | 432
[14 empty] | Slab- GF | 12 | 10 | 1 | 11
[14 empty] | Columns - FF | 432 | 360 | 0 | 360
[14 empty] | Slabs - FF | 12 | 9 | 0 | 9
[14 empty] | Columns - SF | 432 | 108 | 108 | 216
[14 empty] | Slabs - SF | 12 | 1 | 0 | 1
7 |  | Construction of G+3 pattern Houses under JNNURM - BSUP at Ajithsingh Nagar Near Sriram energy plant and at Bhavanipuram near Kabela, Vijayawada, Package-7 |  |  |  | M/s.Vensar Constructions, Hyderabad | 960 | ` 7,34,68,564/- | 12 | 384 | 15/07/2010 | 14/10/2011 | 31/03/2012 | Piles | 1728 | 1393 | 335 | 1728 |  | RCC frame work in 6-Blocks and Earth work excavation in balance 6-Blocks are in progress
[14 empty] | Pile Caps | 432 | 216 | 0 | 216
[14 empty] | Plinth Beams | 12 | 6 | 0 | 6
[14 empty] | Columns - GF | 432 | 216 | 0 | 216
[14 empty] | Slab- GF | 12 | 4 | 0 | 4
[14 empty] | Columns - FF | 432 | 144 | 0 | 144
[14 empty] | Slabs - FF | 12 | 2 | 0 | 2
[14 empty] | Columns - SF | 432 | 36 | 0 | 36
[14 empty] | Slabs - SF | 12 | 0 | 0 | 0
8 | BSUP-Housing Phase-II (97.97 Cr.) | Construction of G+3 pattern Houses under JNNURM - BSUP at Bhavanipuram near Kabela, Vijayawada, Package -8 |  |  |  | M/s.Vensar Constructions, Hyderabad | 960 | ` 7,34,68,564/- | 12 | 384 | 15/07/2010 | 14/10/2011 | 31/03/2012 | Piles | 1728 | 368 | 218 | 586 |  | Excavation of debris and Pile foundation works are in progress.
[14 empty] | Pile Caps | 432 | 0 | 0 | 0
[14 empty] | Plinth Beams | 12 | 0 | 0 | 0
[14 empty] | Columns - GF | 432 | 0 | 0 | 0

## EE-8 - Other (02-06-2012)
VIJAYAWADA MUNICIPAL CORPORATION Circle-VIII
Progress of works as on 02-06-2012
SL.No | Sector | Name of Project | Project Cost | Name of the Work/Package | Estimate Cost Rs. In Lakhs | Agrement amount in Rs. | Name of the contractor | work order / Agreement No. & Date | Date of completion as per Agreement | Expected Date of Completion | Physical Progress |  |  |  |  | Remarks | 1546
[11 empty] | As per Estimate |  | Till Last Week | During this week | Total |  | 5830
[11 empty] | Item | Qty.
1 | Water Supply | Augmentation of watter supply facilities in unserved area | 72.31 Cr. | Construction of Intake well at Gunadala, (Rc.E6/147872/ 08) Work code: 8001 | 123 | 1,04,92,143/- | V.Bogeswara Rao, Ashok Nagar, Guntur. | CE-23-2008-09 Dt.20-08-2009 | 19-02-2010 | 31-10-2011 | - | - | - | - | - | Work tranfered to Executive Engineer-III
1 | Water Supply | Providing sewerage facilities for Northern part of the Vijayawada city | 178.15 Cr. | Providing SWG Sewer lines in Un-served areas of Circle-IV (Nagarjuna Nagar in SriRama Chandra Nagar area and KL Rao Nagar area.) (Rc.E-9/160676/09) Work code: 8006 | 113 | 95,36,635/- | M.Srinivasa rao, Hyderabad | CE-29/2010-11 Dt.15-07-2010 | 14-01-2011 | 31-08-2011 | 150 mm dia | 1749m | 1283m | - | 1283m | Completed | 1283 | 2467
[11 empty] | 200 mm dia | 4081m | 3500m | - | 3500m |  | 3500 | 510
[11 empty] | 250 mm dia | - | 190m | - | 190m |  | 190
[11 empty] | 300mm dia | - | 250m | - | 250m |  | 250
4 | BSUP | Providing basic services in the urban poor in Circle -II & III in 31 Slums | 26.48 Cr. | Construction of 200 KL capacity GLSR at Moghalraj puram Hill area (Rc.EE-III/113561/ 09). Work code: 8002 | 27 | 21,85,930/- | M.Raghavendra Prasad, Vuyyuru. | SE-53/2010-11 Dt.09-09-2010 | 08-01-2011 | - | - | - | - | - | - | Work tranfered to Executive Engineer-III
2 | UGD | Providing sewerage facilities for Northern part of the Vijayawada city | 178.15 Cr. | Providing SWG Sewer lines in Dr. B.R Ambedkar road from Kummaripalem junction to Ramarajya Nagar, (Rc.E-9/167064/09) Work code: 8007 | 47 | 40,46,546/- | M/S K.S.Reddy & Company, Hyderabad. | SE-13-2009-10 Dt.18-02-2010 | 17-08-2010 | 31-03-2011 | 200 mm | 1013m | 1395m | - | 1395m | Completed. | 1395
[11 empty] | 150 mm | 245m | - | - | - |  | 300
[11 empty] | 250 mm | 300m | 300m | - | 300m |  | 6918
[11 empty] | 300 mm | 288m | - | - | -
3 | General | Inundation of One town | VMC funds | Construction of Divertion channel of size 2.0 x 1.50 from Jenda chettu junction to proposed out fall drain at Krishna canal (Rc.E6/117576/10) Work code: 8009 | 185 | 1,32,17,556/- | M/S Chaitanya Constructions, Visakhapatnam. | CE-45-2010-11 Dt.06-08-2010 | 29-12-2010 | 31-12-2011 |  | 675m | 320m | 30m | 350m | 1200 mm dia Rcc NP3 class pipes are being conveyed and laying will be started by 11-06-2012.
4 | General | Water supply - Pipe line works | VMC funds | Providing 355 mm dia HDPE pipe line from Jenda Chettu centre to Gandhiji Municipal High School and 160 mm dia HDPE pipe line from ELSR to Canal road. (Rc.E14-160940/10) | 40 | 3459980.16 | M/S Chaitanya Constructions, Visakhapatnam. | 28-12-2010 | 27-04-2011 | 31-12-2011 | 350mm | 270m | 270m | - | 270m | 350mm dia pipe line completed. 160mm dia pipe line will be taken up along with Diversional Channel.
[11 empty] | 160mm | 270mm | - | - | -
5 | General | Cattle Shed | VMC funds | Construction of Cattle and sheep sheds at Kabela, Vijayawada. (Rc.E14-102353/11) | 9.36 | `855426.37 | Sri. B. Bhargav Kumar, Vijayawada. | 09-03-2011 | 09-06-2011 | 31-10-2011 | - | - | - | - | - | 1 shed completed
6 | General | Compund Wall | VMC funds | Construction of Compound wall to Cattle and sheep sheds at Kabela, Vijayawada. (Rc.E14-130632/11) | 6 | `5,49,597/- | Sri P. Srinivasa Rao | 17-08-2011 | 16-11-2011 | 16-11-2011 | - | - | - | - | - | Compound wall for One shed completed .
7 | General | Infrastructure | 97.98 Cr. | Formation of Rubbish Roads in Housing Lay outs at Ajithsingh Nagar near Sriram Energy Plant and at Bhavanipuram near Kabela. (Rc.E14-127387/10) | 20 | 13.84 | Sri. AVUTU SRINIVASA REDDY, Vijayawada | 19-06-2010 | 18-12-2010 | 31-10-2011 | - | 2524m | 2214m | - | 2214m | Completed at Singh Nagar. Main road is to be formed at Kabela.
1262
27
162

## BRTS
VIJAYAWADA MUNICIPAL CORPORATION | [10 empty] | CIRCLE- III
PHYSICAL AND FINANCIAL STATUS OF WORKS As on 02-06-2012
BRTS ` 152.64 Cr.
SL. No. | Name of the work | Estimate/ Agt Value in `. lakhs | Date of award | NameoftheAgency | Date of Completion as per Agreement | Expected date of Completion | Physical Status | Value of work done ` in lakhs | Expenditure ` in lakhs | Balance to be made ` in lakhs | REMARKS
BRTS Grant 152.64 Cr
1 | Construction of Six lane bridge across Ryves Canal near Madhuranagar Railway gate,Vijayawada City (Rc.EE6/96601/07) | 2253.00 / 2204.00 | 28.02.09 | M/s.Contec Syndicate Pvt.Ltd, Hyderabad. | 27-09-2011 | 31-03-2012 | 100% | 2196 | 1900.8 | 295.2 | Work Completed. | 650 | 475.25 | 174.75
2 | Construction of two lane bridge across Eluru canal near pipula company in Madhuranagar, Vijayawada City (Rc.EE6/96601/07) | 781.00 / 780.50 | 28.02.09 | M/s.Contec Syndicate Pvt.Ltd, Hyderabad. | 27-08-2010 | 30-09-2012 | 65% | 411 | 411 | 0 | Notice issued to the firm to resume the work and to complete the original two lane bridge.
3 | Construction of two lane bridge across Budameru rivulet in Devinagar, Vijayawada City (Rc.EE6/96601/07) | 751.00 / 750.60 | 28.02.09 | M/s.Contec Syndicate Pvt.Ltd, Hyderabad. | 27-08-2010 | 30-09-2012 | 72% | 607 | 607 | 0 | Notice issued to the firm to resume the work and to complete the original two lane bridge. |  |  |  | `
4 | Providing footpaths on SN puram BRTS road | 530.00 / 440.26 | 2009-10-07 | M/S KMV projects,Hyderbad | 10-06-2010 | 30-05-2012 | 75% | 250 | 215 | 35 | Work is in Progress.
5 | Providing street lighting in BRTS road | 180.00 / 126.93 | 22-10-09 | M/S SR communications, Hyderabad. | 23-02-2010 | 30-05-2012 | 80% | 92 | 55 | 37 | Poles erection completed. Lines to be charged.
6 | Providing Road and retaining wall along ryves canal bund from padavala revu to madhura nagar in BRTS road | 825.00 / 785.00 | 22-10-09 | M/S Sidhrtha constructions, Hyderabad. | 31-10-2010 | 31-03-2012 | 100% | 784.96 | 444.96 | 340 | Work Completed.
7 | Providing Kerb and Road markings in BRTS green corridor from Padavalarevu Junction to Ramavarappadu ring (Rc.E14-108935/2011) | 75.00 / 63.51 | 21-10-11 | M/S Polymastic, Kadapa. | 20-04-2012 | 31-05-2012 | 40% | 37 | 27.05 | 26.51 | Work is in Progress.
8 | Providing Ramp in Narlavari street at Madhura nagar bridge. | 12 | - | - | - | - | - | - | - | - | Tender stage
9 | Formation of road from Budameru to Paipula company road via RUB at Singh nagar in feeder corridor (Rc.EE3/108052/2012) | 428 | - | - | - | - | - | - | - | - | Tenders called invited on 26-04-2012. Bids open on 15-05-2012. Evalution is under process.
10 | Formation of Road & Drain from Railway track to Pipula company road to the RUB approaches at Singh Nagar in feeder corridor | 370 | - | - | - | - | - | - | - | - | Tenders received on 16-04-2012. Evalution is under process. (GAD Drawing sent to Railways dept. for approval.
11 | Formation of Feeder Road from Durga puram to Madura nagar bridge via Gulabi tota & road along S/S of Govt. hospital on Ryves canal Bund. | 130 | - | - | - | - | - | - | - | - | Estimate Stage.
12 | Construction of SPV Building along with ITS room by the side of Ryves canal bridge at Madhura Nagar. (Rc.E14-118417/2012) | 50 | - | - | - | - | - | - | - | - | Tender stage
[7 empty] | Total : | 4377.96 | 3660.81 | 733.71

## Sheet1
GF | 20 | 3 | 23 | 8 | 184
FF | 18 | 3 | 21 | 8 | 168
SF | 11 | 3 | 14 | 8 | 112
TF | 5 | 3 | 8 | 8 | 64
[5 empty] | 528 | 2240
528
1712